## Root Access FleetFuel Project -
Title | URL | Assignees | Status | Linked pull requests | Sub-issues progress | Sprint | Estimate | Start date | Target date
Scaffold repo structure and documentation | https://github.com/mirukibs/FleetFuel/issues/9 | mirukibs | Done |  | 2 / 3 (66%) | Sprint 3 |  |  | 2026-07-06
Sprint 1 meeting | https://github.com/mirukibs/FleetFuel/issues/2 | joshuamshana, MfangavoJoel, mirukibs, Mr-Diecan | Done |  |  | Sprint 1 | 8 | 2026-05-20 | 2026-05-20
Project architecture and initial setup | https://github.com/mirukibs/FleetFuel/issues/4 | mirukibs | Done |  |  | Sprint 1 |  | 2026-05-20 | 2026-05-21
Backend implementation of design architecture | https://github.com/mirukibs/FleetFuel/issues/5 | joshuamshana | Done | https://github.com/mirukibs/FleetFuel/pull/14 |  | Sprint 1 | 8 | 2026-05-21 | 2026-05-25
Frontend UI design and implementation | https://github.com/mirukibs/FleetFuel/issues/6 | MfangavoJoel, Mr-Diecan | Done |  |  | Sprint 1 |  | 2026-05-21 | 2026-05-27
API consumption by frontend | https://github.com/mirukibs/FleetFuel/issues/7 | MfangavoJoel, Mr-Diecan | Done |  |  | Sprint 1 |  | 2026-05-25 | 2026-05-27
Create CI workflows to enforce architecture compliance | https://github.com/mirukibs/FleetFuel/issues/8 | mirukibs | Done | https://github.com/mirukibs/FleetFuel/pull/14 |  | Sprint 1 | 3 | 2026-05-22 | 2026-05-27
Scaffold repo structure and documentation | https://github.com/mirukibs/FleetFuel/issues/9 | mirukibs | Done |  | 3 / 3 (100%) | Sprint 3 |  |  | 2026-07-06
Draft project report with architecture notes for sprint 1&2 | https://github.com/mirukibs/FleetFuel/issues/12 | mirukibs | Done |  |  | Sprint 3 |  | 2026-06-24 | 2026-07-05
Implement FleetFuel backend gate | https://github.com/mirukibs/FleetFuel/pull/14 | joshuamshana | Done |  |  | Sprint 1.5
Sprint 2 meeting | https://github.com/mirukibs/FleetFuel/issues/17 | joshuamshana, MfangavoJoel, mirukibs, Mr-Diecan | Done |  |  | Sprint 2 |  | 2026-05-28 | 2026-05-28
Designed and illustrated the fuel procurement module for sprint 2 | https://github.com/mirukibs/FleetFuel/pull/19 | mirukibs | Done |  |  | Sprint 2
Implement sprint 2 design - deliver api endpoints for frontend consumption | https://github.com/mirukibs/FleetFuel/issues/20 | joshuamshana | Done |  |  | Sprint 2 |  | 2026-06-21 | 2026-06-24
Design UI for sprint 2 use cases | https://github.com/mirukibs/FleetFuel/issues/21 | MfangavoJoel | Done |  |  | Sprint 2 |  | 2026-06-22 | 2026-06-24
Consume api endpoints in frontend | https://github.com/mirukibs/FleetFuel/issues/22 | Mr-Diecan | Done |  |  | Sprint 2 |  | 2026-06-24 | 2026-06-27
Design and implement the system's authentication | https://github.com/mirukibs/FleetFuel/issues/28 | joshuamshana | Done |  |  | Sprint 3 |  | 2026-07-04 | 2026-07-06